## Project Sizing Tool
Project Sizing Tool - Planning Phase |  | What are the PMM path should I follow for my project (recommended tools and processes)? | [6 empty] | Rules for sizing:
|  | SMALL PROJECT PMM Recommended | [7 empty] | 1 | 5 | 10
|  | A | B | C | Select A, B, or C for your project | Impact | Score | Medium begins at | 120 | A Points | B Points | C Points
Cost | [7 empty] | Large Begins at | 200
1 | Cost | <$100,000 | $100 - 1M | > $1M | A | 5 | 1 |  |  | 1 | 25 | 50
Time | Time
2 | Time | weeks | months | year | A | 5 | 1 |  |  | 1 | 25 | 50
People
3 | Number People | 1-3 | 3-10 | >10 | A | 5 | 1 |  |  | 1 | 25 | 50
4 | Staff skill set | Experienced | Trained, no experience | No experience | A | 3 | 1 |  |  | 1 | 15 | 30
Scope | Scope |  |  |  |  | 3 |  |  |  | 1 | 15 | 30
5 | Clarity of scope | Clearly defined | Some gray areas | Undefined, vague scope | A | 3 | 1 |  |  | 1 | 15 | 30
Risk | Risk
6 | End User Buy in | Committed end user support | Varying degrees of end user support | End user does not support | A | 2 | 1 |  |  | 1 | 10 | 20
7 | Management Buy in | Committed management support | Varying degrees of management support | Management does not support | A | 3 | 1 |  |  | 1 | 15 | 30
8 | Deadline | No mandated deadline | Internally mandated deadline | Externally mandated, critical deadline | A | 2 | 1 |  |  | 1 | 10 | 20
9 | New Technology vs. Proven, existing Technology | Proven, existing tech in-house | Proven technology but not in house / Not proven but in house expertise | Unproven, new technology that we don't have | A | 3 | 1 |  |  | 1 | 15 | 30
10 | Assumptions | Verified, conservative assumptions | Some gray areas surrounding assumptions | Unverified, aggressive assumptions | A | 2 | 1 |  |  | 1 | 10 | 20
11 | Other Project Specific Risk | Low Risk | Medium Risk | High Risk | A | 2 | 1 |  |  | 1 | 10 | 20
Communication | Communication
Project
12 | Number of departments, people involved | 1 | 2-4 | > 4 | A | 1 | 1 |  |  | 1 | 5 | 10
End User | End User
13 | Number of end users | 25 | 25-100 | >100 | A | 1 | 1 |  |  | 1 | 5 | 10
14 | Change to current work environment, tools and/or process | Minimal change | New technology or new process | New technology and new process | A | 3 | 1 |  |  | 1 | 15 | 30
Integration | Integration
15 | Number of systems | 1 | 2-4 | > 4 | A | 2 | 1 |  |  | 1 | 10 | 20
16 | Number of external project dependencies | Few | Several | Large Number | A | 2 | 1 |  |  | 1 | 10 | 20
17 | Level of complexity | Simple | Medium level of complexity | High level of complexity | A | 2 | 1 |  |  | 1 | 10 | 20
Procurement | Procurement |  |  |  | A
18 | Number of vendors | 1 | 2-3 | > 3 | A | 3 | 1 |  |  | 1 | 15 | 30
19 | MDA's Confidence in Vendor | High | Medium | Low | A | 3 | 1 |  |  | 1 | 15 | 30
A
19
Project Manager Recommended Size |  | Justification - Insert comments here if Project Manager recommended size is different than Sizing Tool Result |  |  | Small