REQUEST FOR PROPOSALS FOR

CONSTRUCTION MANAGER-AT-RISK

#### [INSERT INSTITUTION NAME]

[INSERT PROJECT NAME]

#### RFP No.: [INSERT RFP #]

[INSERT SUBMITTAL DUE DATE]

Prepared By:

[INSERT NAME AND TITLE]

The University of Texas System

Office of Capital Projects [or INSERT NAME of C.I.P. DELIVERY ORGANIZATION]

[INSERT ADDDRESS]

[INSERT CITY, STATE, ZIP]

[INSERT PHONE NUMBER]

[INSERT E-MAIL ADDDRESS]

TABLE OF CONTENTS

Section 1 - General Information & Requirements

  - General Information

  - Public Information

  - Type of Contract

  - Clarifications and Interpretations

  - Submission of Proposals

  - Point-Of-Contact

  - Evaluation of Proposal

  - Owner’s Reservation of Rights

  - Acceptance of Evaluation Methodology

  - No Reimbursement for Costs

  - Certification Required by Texas Governor Executive Order GA-48

Section 2 - Not Used

Section 3 - Requirements for Proposal

  - Respondent’s Pre-Construction Phase Services and Project Execution Plan for this Project

  - Respondent’s Construction Phase Services and Project Execution Plan for this Project

  - Respondent’s Job Site Safety Program for this Project

  - Respondent’s Estimating and Cost Control Measures for this Project

  - Respondent’s Project Planning and Scheduling for this Project

  - Respondent’s Quality Control and Commissioning Program for this Project

  - Respondent’s General Understanding of the U.T. System CM-R Agreement

  - Respondent’s Warranty and Service Support Program for this Project

  - Respondent’s Pricing and Delivery Proposal

Section 4 - Format for Proposals

  - General Instructions

  - Page Size, Binding, Dividers and Tabs

  - Table of Contents

  - Pagination

Request for PROPOsALS For

CONSTRUCTION MANAGER-AT-RISK

#### [INSERT INSTITUTION NAME]

[INSERT PROJECT NAME]

#### RFP No.: [INSERT RFP #]

# SECTION 1 – GENERAL INFORMATION & REQUIREMENTS

  - GENERAL INFORMATION: The University of Texas System (“Owner”) and [INSERT INSTITUTION NAME] are soliciting proposals (“Proposals”) for selection of a Construction Manager at Risk firm for [INSERT PROJECT NUMBER AND NAME] (“Project”), in accordance with the terms, conditions, and requirements set forth in this Request for Proposals.

    - This Request for Proposals (“RFP”) is the second step in a two-step process for selecting a Construction Manager at Risk firm for the Project as provided by Texas Education Code §51.782(e).  The Owner is soliciting RFP’s from five (5) or fewer of the most qualified respondents to the previous RFQ.  The RFP provides the information necessary to prepare and submit Proposals including fee proposals and general conditions prices.  The Owner will rank the Proposals in the order that they provide the “best value” for the Owner based on the published selection criteria and on the ranking evaluations.

    - In the third step of the process, Interviews, the “most” qualified respondents will be requested to attend an interview with the Owner to confirm their Proposal and answer additional questions.  The Owner will then rank the remaining “most” qualified respondents in order to identify a “best value”.

  - Public Information:  All information, documentation, and other materials submitted in response to this solicitation are considered non-confidential and/or non-proprietary and are subject to public disclosure under the Texas Public Information Act (Texas Government Code, Chapter 552.001, et seq.) after the solicitation is completed.

    - The Owner strictly complies with all statutes, court decisions, and opinions of the Texas Attorney General with respect to disclosure of RFP information.

  - Type of Contract:  Any contract resulting from this solicitation will be in the form of the Owner’s Standard Construction Management at Risk Agreement, a copy of which is attached to the previously issued RFQ.

  - CLARIFICATIONS AND INTERPRETATIONS:  Any clarifications or interpretations of this RFP that materially affect or change its requirements will be issued by the Owner as an addendum.  All such addenda issued by the Owner before the Proposals are due are part of the RFP, and respondents shall acknowledge receipt of and incorporate each addendum in its Proposal.

    - Respondents shall consider only those clarifications and interpretations that the Owner issues by addenda five (5) days prior to the submittal deadline shall be considered by respondents.  Interpretations or clarifications in any other form, including oral statements, will not be binding on the Owner and should not be relied on in preparing Proposals.

  - SUBMISSION OF PROPOSALS:

    - [Editor’s Note: Use for hard copy submissions, delte if electronic submission] DEADLINE AND LOCATION: The Owner will receive Proposals until [INSERT MONTH, DAY, YEAR AND TIME] local time at The University of Texas System [INSERT INSTITUTION NAME], [INSERT CITY], Texas, in [INSERT NAME OF BUILDING AND ROOM NUMBER].  Proposals shall be addressed to the Point-of-Contact person identified in Section 1.6 of the previously issued RFQ.

[Editor’s Note: Use for electronic submissions, Delete if hardcopy submission] DEADLINE AND LOCATION: The Owner will receive Proposals until _[INSERT MONTH, DAY, YEAR AND TIME] local time. Proposals shall be addressed to the Point-of-Contact person identified in Section 1.6 of the previously issued RFQ.

    - [Editor’s Note: Use for hard copy submission, delete if electronic submission] Submit [INSERT NUMBER] identical copies of the Proposal.

[Editor’s Note: Use for electronic submissions, delete if hardcopy submission] Submit Proposal files to the OneDrive folder link that the Point-of-Contact has provided.  The Point-of-Contact will contact you directly.

    - Late received Proposals will be returned to the respondent unopened.

    - The Owner will not acknowledge or receive Proposals that are delivered by telephone, facsimile (fax), or electronic mail (e-mail).

    - Properly submitted Proposals will not be returned to respondents.

    - Proposal materials must be enclosed in a sealed envelope (box or container) addressed to the Point-of-Contact person; the package must clearly identify the submittal deadline, the RFP number, and the name and return address of the respondent.

    - Properly submitted Proposals will be opened publicly and the names of the respondents will be read aloud [Editors’ Note:] via a Microsoft Teams meeting coordinated by the Point-of-Contact. [OR INSERT PHYSICAL LOCATION, MONTH, DAY, YEAR AND TIME] local time.

  - POINT-OF-CONTACT:  Refer to the previously issued RFQ.

  - EVALUATION OF PROPOSAL:  The evaluation of the Proposals shall be based on the Respondent’s actual Pre-Construction Phase Fee, Construction Phase Fee, General Conditions and other requirements as described in this RFP.  All properly submitted Proposals will be reviewed, evaluated, and ranked by the Owner.

  - OWNER’S RESERVATION OF RIGHTS:  The Owner may evaluate the Proposals based on the anticipated completion of all or any portion of the Project.  The Owner reserves the right to divide the Project into multiple parts, to reject any and all Proposals and re-solicit for new Qualifications or Proposals, or to reject any and all Proposals and temporarily or permanently abandon the Project.  Owner makes no representations, written or oral, that it will enter into any form of agreement with any respondent to this RFP for any project and no such representation is intended or should be construed by the issuance of this RFP.

  - Acceptance of Evaluation Methodology:  By submitting its Proposal in response to this RFP, respondent accepts the evaluation process and acknowledges and accepts that determination of the “best value” firm will require subjective judgments by the Owner.

  - no reimbursement for costs:  Respondent acknowledges and accepts that any costs incurred from the respondent’s participation in this RFP shall be at the sole risk and responsibility of the respondent.

  - CERTIFICATION REQUIRED BY TEXAS GOVERNOR EXECUTIVE ORDER GA-48:  Pursuant to Executive Order GA-48 of the Governor of Texas effective November 19, 2024, Contractor certifies that it and, if applicable, any of its holding companies or subsidiaries, is not:

a.           Listed in Section 889 of the 2019 National Defense Authorization Act (NDAA); or

b.           Listed in Section 1260H of the 2021 NDAA; or

c.           Owned by the government of a country on the U.S. Department of Commerce's foreign adversaries list under 15 C.F.R. § 791.4; or

d.          Controlled by any governing or regulatory body located in a country on the U.S. Department of Commerce's foreign adversaries list under 15 C.F.R. § 791.4.

[NOTE: Executive Order GA 48 states that a public institution of higher education cannot enter into a new contract, contract extension, or contract renewal for a good or service with any company that meets any of the above-listed criteria. However, if the public institution of higher education can sufficiently demonstrate that (a) the good or service is necessary for the institution of higher education to fulfill a core function that directly benefits Texans and (b) the good or service can only be provided by an entity that meets one of the above-listed criteria, then the public institution of higher education may enter into a new contract, contract renewal, or contract extension with such an entity for no more than one year from November 19, 2024, and never thereafter.]

SECTION 2 – (NOT USED)

## SECTION 3 – REQUIREMENTS FOR PROPOSAL

Respondents shall carefully read the information contained in the following criteria and submit a complete response to all questions in Section 3 formatted as directed in Section 4.  Incomplete responses will be considered non-responsive.

  - CRITERIA ONE: Respondent’s Pre-construction Phase SERVICES and Project Execution Plan for this Project

    - Describe your Construction Management and Execution Plan for providing Pre-Construction Phase Services required for this Project.

    - Reconfirm in graphic form the proposed Project assignments, lines of authority and communication for each member and the estimated percent of time these individuals will be involved in this Project for Pre-Construction Services. Clearly identify any changes / revisions via highlighted text or graphics from the information previously submitted in response to RFQ Section 3.3.

    - Describe your philosophy for maximizing Project scope and minimizing Project risk during Pre-Construction Services.

    - Describe what you perceive are the critical Pre-Construction issues for this Project?

    - Identify the personnel on your team responsible for reviewing all design and construction documents and for providing written feedback / analysis regarding cost, schedule and constructability to the Owner and the Project Architect / Engineer and its consultants. Describe the procedures, processes and objectives your personnel will employ regularly on this project to complete these deliverables in a timely manner.

    - Describe your plans to interface with the Architect / Engineer and its consultants to enhance the design and planning process for this Project.

    - The Owner expects your Constructability Program to maintain the project budget without sacrificing quality, eliminate scope gaps and resolve discrepancies as well as assist in the development of prudent design solutions. Describe how your Constructability Program will meet these expectations and be reported in the form of reoccurring deliverables to the Owner and the Project Architect / Engineer and their consultants during the Project.

[EDITOR’S NOTE : OPTIONAL QUESTIONS – DELETE UNUSED QUESTIONS]

    - Provide examples of records, reports, logs, monitoring systems, and information management systems you will use on this Project during Pre-Construction Services. [Editor’s Note: Consider having the examples be an Appendix to the RFP submission and not count towards the total maximum page limitation indicated in Section 4, clarify accordingly]

    - If the Construction Manager at Risk can demonstrate and if Owner determines it advantageous to the Project, the Owner may consider allowing the Construction Manager at Risk to award sub-contracts prior to completion of Issue for Construction Documents. If allowed by the Owner what sub-contractors / trades would you propose for early award packages and at what stages of document completion?   How would you ensure the Project, nor the Owner are being exposed to unnecessary risk and budgets being sacrificed?

    - Describe your Bid/Proposal Package Strategy and methods for advertising and receiving proposals from qualified and experienced subcontractors, vendors, suppliers, etc. Identify how scope confirmation between respondent proposals will be accomplished for securing a firm cost of work and recommending award to the Owner and awarding contracts thereafter. Identify how you will include Owner in this process, with respect to Owner’s Project Administration Specification Section 01 31 00 (attached to the previously issued RFQ).

    - Provide any other details regarding special services, products, advantages, or other benefits offered to the Owner by the Respondent that are included as part of this Proposal. If any of the special services, products, advantages, or other benefits are in “addition to” clearly state which items are an additional service to the proposal.

3.2	CRITERIA two: Respondent’s Construction Phase SERVICES and Project Execution Plan for this Project

    - Describe your Construction Management and Execution Plan for providing Construction Phase Services required for this Project.

    - Reconfirm in graphic form the proposed Project assignments, lines of authority and communication for each member and the estimated percent of time these individuals will be involved in this Project for Construction Services. Clearly identify any changes / revisions via highlighted text or graphics from the information previously submitted in response to RFQ Section 3.3.

    - Describe what you perceive are the critical construction issues for this Project?

    - Describe your ability and desire to self-perform work on this Project, and the method for determining yourself as the “best value” through a competitive proposal process that complies with the Agreement Between Owner and Construction Manager at Risk.

[EDITOR’S NOTE : OPTIONAL QUESTIONS – DELETE UNUSED QUESTIONS]

    - Provide examples of records, reports, logs, monitoring systems, and information management systems you will use on this Project during Construction Services. [Editor’s Note: Consider having the examples be an Appendix to the RFP submission and not count toward the total maximum page limitation indicated in Section 4, clarify accordingly]

    - Describe your plans for infection control in an occupied, fully functional hospital facility.

    - Describe you approach for mitigating [Editor’s Note: MODIFY AS APPROPRIATE] noise / vibration, dust / fume / odor / moisture / temperature transmission into adjacent occupied [Editor’s Note: MODIFY AS APPROPRIATE] space / area / floor / facility / building / property.

    - Describe your approach to containing storm water run-off and meeting the regulatory requirements of the Texas Commission on Environmental Quality’s (TCEQ) Texas Pollutant Discharge Elimination System (TPDES) General Construction Permit No. TXR150000 and The University of Texas System’s Storm Water Pollution Prevention Program for projects that will disturb land. [Editor’s Note: Include this question if the project involves disturbing earth]

    - Describe your approach to prevent tracking of soil materials beyond the limits of construction, especially onto roads, drives and sidewalks and how you will immediately clean up such tracking instances when they occur. [Editor’s Note: Include this question if the project involves disturbing earth]

    - Describe your process for incorporating Building Information Models (BIM) into this Project and which sub-contractors / trades would be included in the BIM effort and the Level of Detail / Development model each will provide. Identify the benefits and advantages the BIM effort will provide this project.

    - Describe your approach to pre-planning and coordinating inspections and approvals with the Owner’s work force and consultants.

    - Describe your approach to coordinating inspections and approvals with the Texas Department of Licensing and Regulation regarding Texas Accessibility Standards.

    - Describe your approach to pre-planning and coordinating inspections and approvals with the Texas Department of Licensing and Regulation regarding elevator systems.

    - Describe your approach to pre-planning and coordinating inspections and approvals with the State Fire Marshall regarding fire / life safety systems.

    - Describe your approach to pre-planning and coordinating inspections and approvals with the Owner’s work force/consultants and other AHJ entities, including but not limited to, Texas Department of Licensing and Regulation, State Fire Marshall, etc.

    - Provide the name of the Project Management System you will utilize for construction, as required by the Owner’s Special Conditions (attached to the previously issued RFQ).

    - Provide any other details regarding special services, products, advantages, or other benefits offered to the Owner by the Respondent that are included as part of this Proposal. If any of the special services, products, advantages, or other benefits are in “addition to” clearly state which items are an additional service to the Proposal.

  - CRITERIA THREE:  RESPONDENT’S job site safety program FOR THIS PROJECT

The vision of the University of Texas System and this Institution is to prevent workplace injuries / incidents on all construction projects. We consider this a core value within our organization and attach maximum importance to this Criteria in the evaluation.

*** Note: Criteria Three shall be developed solely by the Respondent’s Corporate Safety Officer / Director and at the end of Criteria Three attest to the responses by signature. Your response to this criterion will be reviewed by the Owner’s representatives and The University of Texas System – Office of Risk Management Safety Professional.

    - Briefly explain your firm’s understanding of the UTS Project Safety Requirements 01 35 23 and indicate how your project safety program will align with the specification. * Note – Generic statements such as “have read and understand the safety specification” or “will comply” are not acceptable responses.

    - Briefly explain how your firm and specifically the Corporate Safety Officer / Director will ensure that project safety professional(s) will be vetted for building construction safety experience, continuing education, and past performance prior to proposing candidates to the Owner for Guaranteed Maximum Price inclusion in preparation of issuance of Notice to Proceed with Construction or anytime thereafter for the Project Safety Coordinator (PSC) and Project Safety Assistant (PSA) positions.

    - Briefly explain how your firm and specifically your Corporate Safety Officer / Director will ensure that the onsite PSC and any PSA will have no other duties on the project except safety. Detail what safety administration duties will be provided by others and by whom.

    - Briefly explain how your firm and specifically the Corporate Safety Officer / Director will ensure that the PSC and/or required number of PSAs will be onsite as indicated by the UTS Project Safety Requirements 01 35 23. Detail the process for and how backup replacements for the PSC and / or PSA(s) will be provided for scheduled time off and emergencies.

    - Briefly explain your firm’s and specifically the Corporate Safety Officer / Director’s expectations for actual percentage of time spent in the field by the PSC and each PSA actively engaged in safety oversight of ongoing project work activities and workers.

    - Briefly indicate how your firm and specifically the Corporate Safety Officer / Director will support the onsite PSC and PSA(s) when safety issues arise.  Based on reporting line for the PSC, what level of corporate safety will periodically audit the project and how often? How often is it anticipated that the Corporate Safety Officer / Director will periodically audit the project?

    - Provide the signature of the Respondent’s Corporate Safety Officer / Director attesting to CRIITERIA THREE responses.

  - CRITERIA FOUR:  RESPONDENT’S ESTIMATING AND COST CONTROL MEASURES FOR THIS PROJECT

    - Identify the proposed Pre-Construction and Construction Phase Services cost estimating resources (i.e., hardware, software etc.) to be used on this Project.

    - The Owner requires that the Construction Manager at Risk to provide continuous cost estimating throughout the project, with the ability to provide the Owner with the current anticipated project costs at any point during the design phases of the project, not just at the end of each phase.  Describe your cost estimating approach and reporting methods to achieve this criteria.

    - Describe how you will work collaboratively with the Project Architect / Engineer and their consultants to reconcile construction cost estimates and report the efforts of the reconcilation process to the Owner.

    - The Owner requires a final signed Guaranteed Maximum Price (GMP) Proposal from the Construction Manager at Risk [Editor’s Note: SELECT ONE] at 100% Design Development [OR] XX% Construction Documents.  Describe 1)  Your process for ensuring that the GMP Proposal Documents provide the information necessary to arrive at a complete and accurate GMP that is within the Owner’s budget includes all Owner requirements, 2) The contingencies you will propose, how those are justified, then managed through the completion of the Construction Phase Services, and 3) Your process for identifying and mitigating risks to the Owner within the GMP, 4) Your process for subsequently ensuring that the 100% Issue for Construction Documents align with the project scope and schedule in the previously accepted GMP Proposal Documents.

    - Other than implementation of the Owner’s Standard Schedule of Values Template provided in Project Administration Specification Section 01 31 00, describe your plans and processes for establishing, monitoring, tracking, and reporting the Guaranteed Maximum Price Proposal during the procurement and payment process.

    - Describe your plans and processes for vetting of potential Change Proposals for legitimacy, contractual compliance, accuracy, and timeliness prior to notifying the Owner of the potential change and subsequently presenting Change Proposals for Owner review.

[EDITOR’S NOTE OPTIONAL QUESTIONS – DELETE UNUSED QUESTIONS]

    - The Owner has specific system design and construction standards and specification requirements for construction projects but is committed to exploring more cost-effective ways to meet these requirements.  In working with a Project Architect/Engineer during both preconstruction and construction submittal phase, describe how you propose to creatively work toward the most cost-effective achievement of the Owner’s goals for this project considering not only initial cost, but Total Cost of Ownership.  For any combination of three (3) projects listed in response to Section 3.4 or 3.5 of previously submitted RFQ, provide examples of how you have been able to achieve Total Cost of Ownership benefits for the Owner.

    - Describe your philosophy regarding Payment and Performance bonds required by the Owner on this project, and the bonds your firm requires of subcontractors.

  - CRITERIA FIVE: RESPONDENT’S Project PLANNING AND scheduling FOR THIS PROJECT

    - Identify the specific resources (i.e., hardware, software, etc.) to be used on this Project with respect to Owner’s Project Planning and Scheduling Specification Section 01 32 00 (attached to the previously issued RFQ).

    - Provide a Primavera CPM Milestone schedule for this Project as described in Owner Project Planning and Scheduling Specification Section 01 32 00 using the Project Planning Schedule in the previously issued RFQ and identify specific critical process, phases, milestones, approvals, and procurements anticipated.  Clearly identify the 10% Total Project Float required during the Construction Phase. State your commitment to this schedule. [Editor’s Note: Consider having the examples be an Appendix to the RFP submission and not count toward the total maximum page limitation indicated in Section 4, clarify accordingly]

    - Identify the schedule assumptions that are included in your CPM schedule submitted for this Project.

    - Understanding the Owner’s Project Planning and Scheduling Specification Section 01 32 00 describe your philosophy regarding establishment and use of Total Project Float for this Project to achieve the Owner’s required Substantial Completion date.

    - Describe your plan for meeting or improving the Owner’s proposed schedule for design and/or construction.  If you propose to improve the schedule, describe any impact on quality of services, materials or workmanship that may occur.

[EDITOR’S NOTE: OPTIONAL QUESTIONS – DELETE UNUSED QUESTIONS]

    - This Project will physically connect to an existing adjacent building that will remain occupied during construction, describe your plan to phase construction to minimize impact to the occupants in the existing building.

    - Describe the anticipated steps necessary to maintain operation of the occupied building during construction.

  - CRITERIA SIX: RESPONDENT’S quality control, COMMISSIONING prOGRAM AND CLOSEOUT FOR THIS PROJECT

    - Describe how the Commissioning Coordinator on your staff will work in conjunction with the Owner’s commissioning agents, Owner’s inspectors, Owner’s test and balance firm, Authorities Having Jurisdiction, and the Project’s design team.

    - Describe how your quality control team will measure the quality of construction and commissioning performed by all subcontractors as required by Owner Specification Sections 01 45 00 Project Quality Control and 01 91 00 General Commissioning Requirements and how will you address non-conforming work on this Project. Identify how you will document and report the deficiencies and deficiency resolution to the Owner prior to requesting the Owner’s work forces or consultant’s participation in inspections and testing of systems or development of punch lists.

    - Describe your implementation of a quality control process for this Project during the Design Development stage through completion of Construction Documents stage.

[EDITOR’S NOTE: OPTIONAL QUESTIONS – DELETE UNUSED QUESTIONS]

    - Describe how and when you will implement the Owner’s Commissioning Specification 01 91 00 and Project Closeout Procedures Specification 01 77 00 on this Project.

    - Describe your quality and schedule approach to pre-fabrication and off-site assembly. Describe the opportunities you see as benefits or deficits for this proposed project. Briefly describe the scopes of work that have been successfully prefabricated or assembled off-site on similar projects.

    - Describe how you intend to create, track, complete and close out punch lists for this Project. Further describe after you have created your punch list for this Project how you then intend to incorporate the punch lists subsequently created by the Project’s design team and Owner’s consultants and how those items are then closed out as complete by those respective parties.

    - Describe your understanding of the Owner’s requirement for, Certification of No Asbestos Containing Materials or Work and identify how this will be managed on this Project.

    - Describe how and when you intend to facilitate mock-ups for Owner’s approval into the Project.

    - Outline the process you intend to utilize during construction for continuously maintaining accurate, professionally drafted electronic As Built / Record Documents for turn over to the design team and the Owner.

  - CRITERIA SEVEN:  REPONDENT’S GENERAL UNDERSTANDING OF THE U.T. SYSTEM CM-R AGREEMENT

    - Identify any terms of the Agreement that you will ask to change before signing The U.T. System Construction Manager at Risk Agreement.

    - Provide a detailed list of all Pre-Construction Services and associated deliverables you will provide to the Owner and the Project Architect / Engineer and their consultants on this Project.

    - Provide a detailed list of all Construction Services and associated deliverables you will provide to the Owner and the Project Architect / Engineer and their consultants on this Project.

    - State your understanding of your obligations to pay trade contractors, suppliers, and vendors etc. on this Project.

    - Describe your understanding of the audit requirements.

    - Describe your understanding of the Agreement with respect to the Owner’s responsibility for payment of the GMP line items and costs within those line items.

[EDITOR’S NOTE: OPTIONAL QUESTIONS – DELETE UNUSED QUESTIONS]

    - In response to CRITERIA 9 of this RFP clearly identify any scope you have excluded from the Allowable General Conditions Line Items as provided for in the Agreement Between Owner and Construction Manager-At-Risk, Exhibit “C” and state the reason for each item’s exclusion.

3.8	CRITERIA EIGHT: RESPONDENT’S Warranty AND Service Support PROGRAM FOR THIS PROJECT

    - Describe your warranty service support philosophy and warranty service implementation plan for this Project.

    - State your understanding of the time allotted to promptly remedy defects once notified by the Owner.

    - Describe how you will measure the quality of service provided to the Owner for this Project.

[EDITOR’S NOTE: OPTIONAL QUESTIONS – DELETE UNUSED QUESTIONS]

    - Provide reference letters from three (3) Owners identified in Sections 3.4 or 3.5 of the previously issued RFQ that describe your response to, and performance on, warranty services AFTER substantial completion. Reference letters but be no older than 5 years.

3.9	CRITERIA NINE:  REPONDENT’S PRICING AND DELIVERY PROPOSAL

    - Complete the attached “Pricing and Delivery Proposal” form.

CRITERIA NINE:  RESPONDENT’S PRICING AND DELIVERY PROPOSAL

Proposal of:

(Respondent’s Company Name)

To:		Kevin Eltife, Chairman

The Board of Regents

The University of Texas System

Austin, Texas

Project Name:	[INSERT PROJECT NAME]

RFP No.: 	[INSERT PROJECT No.]

Having carefully examined all the requirements of the previously issued RFQ, this RFP, the proposed form of Agreement, and any attachments to them, the undersigned proposes to furnish Construction Manager-At-Risk services as required for this Project on the following terms:

    - ESTABLISHEMENT OF THE Construction Manager’s Budget Limitation:  The Owner has established a Construction Manager’s Budget Limitation (CMBL) amount of $[INSERT AMOUNT], which includes the Pre-Construction Phase Fee and the Construction Services Guaranteed Maximum Price Proposal.

    - RESPONDENT’S PRE-CONStruction Phase Fee:  The Respondent shall identify a Pre-Construction Phase Fee, pursuant to Article 5 of the Agreement.

| Respondent’s Pre-Construction Phase Fee | $ |
| --- | --- |

    - ESTABLISHEMENT OF THE Construction cost limitation:  Using the CMBL and the Respondent’s Pre-Construction Phase Fee identified above, the Respondent shall identify the Construction Cost Limitation (CCL), pursuant to Article 3 of the Agreement:

| Construction Manager’s Budget Limitation | $ [INSERT AMOUNT] |
| --- | --- |
|  | (less) |
| Owner’s Construction Contingency | $ [INSERT AMOUNT] |
|  | (less) |
| Owner’s Special Cash Allowance | $ [INSERT AMOUNT] |
|  | (less) |
| Respondent’s Pre-Construction Phase Fee (as identified above) | $ |
|  | (equals) |
| Respondent’s Construction Cost Limitation | $ |

    - RESPONDENT’S Construction Phase Fee:  Using the CCL identified above, the Respondent shall identify a Construction Phase Fee percentage, pursuant to Article 14 of the Agreement:

| Respondent’s Construction Phase Fee Percentage | % |
| --- | --- |
|  | (equals) |
| Respondent’s Estimated Construction Phase Fee Amount (percentage times the CCL above) | $ |

    - RESPONDENT’S NOT-TO-EXCEED General Conditions Costs: Using the Project Planning Schedule included in Section 2.5 of the previously issued RFQ, the Respondent shall identify a General Conditions not-to-exceed percentage and amount as defined by Article 13 and exhibit of the Agreement, the Uniform General Conditions, Owner’s Special Conditions with Attachments and Owner Specification Sections 007316, 013100, 013200, 013523, 014500, 015723, 017700, 019100, 101416.11

| Respondent’s General Conditions Percentage | _____________ % |
| --- | --- |
|  | (equals) |
| Respondent’s Estimated General Conditions (percentage times the CCL above) | $ |
| Total Construction Duration (Notice To Proceed for Construction to Final Completion as identified in Section 2.5 of the previously issued RFQ) | NUMBER months |

      - Using the not-to-exceed General Conditions costs identified above, the Respondent shall identify all project management, bonds, insurance, field office and office supply costs for the Project as listed below:

| Allowable General Condition Line Item Category |  | Estimated Total Cost |  |  |
| --- | --- | --- | --- | --- |
| On-Site Project Management Staff | subtotal |  | $ |  |
| Bonds and Insurance | subtotal |  | $ |  |
| Temporary Project Utilities | subtotal |  | $ |  |
| Field Offices & Office Supplies | subtotal |  | $ |  |

Estimated On-Site Project Management Staff and Rates

| Position |  | Quantity |  | Months |  | Monthly Salary Rate |
| --- | --- | --- | --- | --- | --- | --- |
| Project Executive |  |  |  |  |  | $ |
| Project Manager |  |  |  |  |  | $ |
| Superintendent(s) |  |  |  |  |  | $ |
| Assistant Superintendent(s) |  |  |  |  |  | $ |
| Project Engineer/Expeditor(s) |  |  |  |  |  | $ |
| Field/Office Engineer(s) |  |  |  |  |  | $ |
| Field Support Staff |  |  |  |  |  | $ |
| BIM Coordinator |  |  |  |  |  | $ |
| CPM Scheduler |  |  |  |  |  | $ |
| MEP/CX Coordinator(s) |  |  |  |  |  | $ |
| Safety Coordinator(s) |  |  |  |  |  | $ |
| Safety Assistant(s) |  |  |  |  |  | $ |

[Editor’s Note: Optional - Contact OCP for detailed Pricing and Delivery Exhibit – General Conditions Breakdown - for respondent’s submission to obtain additional information about the above values and durations. This spreadsheet should be submitted as an excel document as part of the appendix and not count as a printed page. Clarify in Section 4]

Respondent shall complete and submit the Criteria 9 Pricing and Delivery Allowable General Conditions Spreadsheet as an Appendix to the Proposal

    - addenda:  Receipt is hereby acknowledged of the following addenda to this RFP (initial if applicable).

No. 1 _____	No. 2 _____	No. 3 _____	No. 4 _____	No. 5 _____	No. 6 _____

    - AWARD OF CONTRACT AND COMMENCEMENT OF SERVICES:  The undersigned agrees to execute the Contract after notification that the Respondent has been identified by the Owner as the Respondent with the “best value” Proposal, and to commence services on or before the commencement date stated by the Owner in a Notice to Proceed.  The Owner reserves the right to accept or reject and all Proposals and to waive proposal irregularities.  Proposals shall be valid and not withdrawn for a period of ninety (90) days from the date of opening thereof.

    - Respectfully Submitted and Certified By:

_________________________________	________________________________

(Respondent’s Printed Name)				(Title)

_________________________________	________________________________

(Authorized Signature)				(Date)

SECTION 4 – FORMAT of PROPOSALS

  - General Instructions

    - Proposals shall be prepared simply and economically, providing a straightforward, concise description of the respondent's ability to meet the requirements of this RFP.  Emphasis shall be on the quality, completeness, clarity of content, responsiveness to the requirements, and an understanding of Owner's needs.

    - [Editor’s Note: For hard copy submissions, DELETE IF ELECTRONIC SUBMISSION, align with Section 1.5] Proposals shall be a MAXIMUM of fifty (50) printed pages. Minimum eleven (11) point font size shall be used. The cover, table of contents, divider sheets, and Pricing and Delivery Proposal do not count as printed pages. Additionally, the General Conditions Breakdown spreadsheet and Appendix items listed in 3.1.8, 3.2.5, and 3.5.2 do not count as printed pages.

[Editor’s Note: For electronic submissions, DELETE IF HARD COPY SUBMISSION, align with Section 1.5] Electronically submitted Proposals shall be a searchable .pdf and a MAXIMUM OF FIFTY (50) PRINTABLE PAGES.  Minimum eleven (11) point font size shall be used. The cover, table of contents, divider sheets, and Pricing and Delivery Proposal do not count as printed pages.  Additionally, the General Conditions Breakdown spreadsheet and Appendix items listed in 3.1.8, 3.2.5, and 3.5.2 do not count as printed pages.

    - Respondents shall carefully read the information contained in this RFP and submit a complete response to all requirements and questions as directed.  Incomplete Proposals  will be considered non-responsive and subject to rejection.

    - Proposals and any other information submitted by respondents in response to this RFP shall become the property of the Owner.

    - Proposals that are qualified with conditional clauses, alterations, items not called for in the RFP documents, or irregularities of any kind are subject to rejection by the Owner, at its option.

    - The Owner makes no representations of any kind that an award will be made as a result of this RFP.  The Owner reserves the right to accept or reject any or all Proposals , waive any formalities or minor technical inconsistencies, or delete any item/requirements from this RFP when deemed to be in Owner's best interest.

    - Proposals shall consist of answers to questions identified in Section 3 of the RFP.  It is not necessary to repeat the question in the Proposals; however, it is essential to reference the question number with the corresponding answer.

    - Failure to comply with all requirements contained in this Request for Proposals may result in the rejection of the Proposals.

  - PAGE SIZE, BINDING, DIVIDERS, AND TABS:

    - [Editor’s Note: Use for hard copy submission, DELETE IF ELECTRONIC SUBMISSION] Proposals shall be printed on letter-size (8-1/2” x 11”) paper, portrait orientation and assembled with spiral-type bindings or staples. DO NOT USE METAL-RING HARD COVER BINDERS.

[Editor’s Note: Use for electronic submissions, DELETE IF HARD COPY SUBMISSION] Proposals submitted electronically shall be formatted to be printed on letter-size (8-1/2” x 11”) paper.

    - Additional attachments shall NOT be included with the Proposals.  Only the responses provided by the Respondent to the questions identified in Section 3 of this RFP will be used by the Owner for evaluation. [Editor’s Note: Align with Section 3 and 4.1.2] The General Conditions Breakdown spreadsheet and Appendix items listed in 3.1.8, 3.2.5, and 3.5.2 are exempt from this limitation.

    - [Editor’s Note: Use for hard copy submission, DELETE IF ELECTRONIC SUBMISSION] Separate and identify each criteria response to Section 3 of this RFP by use of a divider sheet with an integral tab for ready reference.

[Editor’s Note: Use for electronic submissions, DELETE IF HARD COPY SUBMISSION] Separate and identify each criteria response to Section 3 of this RFP by use of bookmarks in the .pdf file.

  - TABLE OF CONTENTS:

    - Submittals shall include a “Table of Contents” and give page numbers for each part of the Proposal.

  - PAGINATION:

    - Number all pages of the submittal sequentially using Arabic numerals (1, 2, 3, etc.).